## Scope List Original (hidden)
DSM 2013 On-boarding Plan |  |  | MAY |  |  |  |  | JUN |  |  |  | JUL |  |  |  |  | AUG |  |  |  | SEP |  |  |  | OCT |  |  |  |  | NOV |  |  |  | DEC
|  |  | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | CIO Commitment
| MC Petrolook | PT | [35 empty] | YES | bar: MAY 18 to MAY 20
| MC Sigma | UI | [35 empty] | YES | bar: MAY 18 to JUN 24
| MC GFM | GF | [35 empty] | YES | bar: MAY 18 to JUN 24
| AGRisk | GF | [35 empty] | YES | bar: MAY 18 to JUN 24
| Quantum | GF | [35 empty] | YES | bar: MAY 18 to JUN 24
| ArcSight | ITSO | [35 empty] | YES | bar: MAY 18 to JUN 24
| GLS Toolset | PT | [35 empty] | YES | bar: MAY 18 to MAY 22
| SAP::CRM::CHM | DS | [35 empty] | YES | bar: MAY 18 to MAY 20
| Global ICEBOX (P2 & P4 instances) | DS | [35 empty] | YES | bar: MAY 18 to JUN 24
| SHARE St. Rose | DS | [35 empty] | YES | bar: MAY 19 to JUN 26
| SPOTFIRE MC | PT | [35 empty] | YES | bar: MAY 19 to JUN 26
| Shell People Business Warehouse | GF | [35 empty] | YES | bar: MAY 20 to JUL 27
| SHELL PEOPLE HR Reporting | GF | [35 empty] | YES | bar: MAY 20 to JUL 27
| Financial Closing Cockpit (FCC) | GF | [35 empty] | YES | bar: MAY 20 to JUL 27
| TSI | GF | [35 empty] | YES | bar: MAY 20 to JUL 27
| Endur Oil | TR | [35 empty] | YES | bar: MAY 20 to JUL 27
| ODW | TR | [35 empty] | YES | bar: MAY 20 to JUL 27
| ERS - Enterprise Reporting Solution (ERS) | GF | [35 empty] | YES | bar: MAY 22
| EDI Hub/ E Banking Hub | GF | [35 empty] | YES | bar: JUN 23 to JUL 30
| ENOM | TR | [35 empty] | YES | bar: JUN 23
| Energy Components (ALTAMIRA) | UI | [35 empty] | YES | bar: JUN 24 to JUN 26
| BSI Tax Factory | GF | [35 empty] | YES | bar: JUN 24 to JUL 31
| MC Sharepoint | ITSO | [35 empty] | YES | bar: JUN 25 to AUG 32
| SAP US Magellan Syst | DS | [35 empty] | YES | bar: JUN 25 to OCT 40
| SAP US Luminon BW Syst | DS | [35 empty] | YES | bar: JUN 25 to OCT 40
| SAP US Luminon Syst | DS | [35 empty] | YES | bar: JUN 25 to OCT 40
| SAP US Simon Bolt | DS | [35 empty] | YES | bar: JUN 25 to OCT 40
| SABRIX (Munich) | GF | [35 empty] | YES | bar: JUN 25 to AUG 32
| Sharepoint 2010 | ITSO | [35 empty] | YES | bar: JUN 25 to AUG 32
| eMarketplace Suite | TR | [35 empty] | YES | bar: JUN 26
| Ergonomed | DS | [35 empty] | YES | bar: JUL 27 to AUG 34
| SODA | TR | [35 empty] | YES | bar: JUL 27 to AUG 34
| TRIM (non-MC) | GF | [35 empty] | YES | bar: JUL 27 to AUG 34
| Energy Components (GABON) | UI | [35 empty] | YES | bar: JUL 27 to JUL 29
| BOS (Red Prairie Retail - Head Office) | DS | [35 empty] | YES | bar: JUL 28 to AUG 35
| SAP BUSINESS WAREHOUSE | UI | [35 empty] | YES | bar: JUL 28 to AUG 35
| Energy Components (KASHAGAN) | UI | [35 empty] | YES | bar: JUL 28 to JUL 30
| CONVERGE | UI | [35 empty] | YES | bar: JUL 29 to SEP 36
| Shell eServe | DS | [35 empty] | YES | bar: JUL 29 to SEP 36
| eHaulier | DS | [35 empty] | YES | bar: JUL 29 to SEP 36
| Customer Setup and Amend | DS | [35 empty] | YES | bar: JUL 30 to SEP 37
| Deal Management and Pricing Tool - DMAP | DS | [35 empty] | YES | bar: JUL 30 to SEP 37
| Contract Management System - Upside | GF | [35 empty] | YES | bar: JUL 31 to SEP 38
| Enterprise Business Objects Service (eBOSS) | GF | [35 empty] | YES | bar: JUL 31 to SEP 38
| Energy Components (EC-SEIC) | UI | [35 empty] | YES | bar: AUG 32 to AUG 34
| Vertex Bolt-on | DS | [35 empty] | YES | bar: AUG 32
| Energy Components (SPEX) | UI | [35 empty] | YES | bar: AUG 32 to AUG 34
| SAP GRC (PG4) | GF | [35 empty] | YES | bar: AUG 33 to OCT 40
| Collective (Archer) | GF | [35 empty] | YES | bar: AUG 33 to OCT 40
| Identity Management Service (IMS) | GF | [35 empty] | YES | bar: AUG 35 to OCT 42
| Identity Provider Service (IDP) | GF | [35 empty] | YES | bar: AUG 35 to OCT 42
| KSTAT | TR | [35 empty] | YES | bar: AUG 35 to OCT 42
| Global Production Dashboard | UI | [35 empty] | YES | bar: AUG 35 to OCT 42
| Energy Components (WGTEC-EC-UIE) | UI | [35 empty] | YES | bar: AUG 35 to SEP 37
| Energy Components (MAJNOON) | UI | [35 empty] | YES | bar: SEP 36 to SEP 38
| Elemica Base | DS | [35 empty] | YES | bar: SEP 36 to OCT 43
| ProWatch (new servers) | GF | [35 empty] | YES | bar: SEP 36 to OCT 43
| Energy Components (STOS90) | UI | [35 empty] | YES | bar: SEP 38 to OCT 40
| Energy Components (QSGTL) | UI | [35 empty] | YES | bar: SEP 39 to OCT 41
| Energy Components (SPD) | UI | [35 empty] | YES | bar: SEP 39 to OCT 41
| Simcorp Dimension including Batch processes, Models and PIP | GF | [35 empty] | YES | bar: OCT 40 to NOV 47
| SWIFT (SAMCO) | GF | [35 empty] | YES | bar: OCT 40 to NOV 47
| LIFETIME | GF | [35 empty] | YES | bar: OCT 40 to NOV 47
| Pearl SAMCO including Batch processes | GF | [35 empty] | YES | bar: OCT 40 to NOV 47
| SABRIX | DS | [35 empty] | No (want DBR reports asap)
| SAP P49 GP-GTL | DS | [35 empty] | NO (may start in 2013)
| FPS | DS | [35 empty] | No (may start at end 2013)
| MS BizTalk | DS | [35 empty] | NO (may start in 2013)
| FileNet Image Manager GLB | DS | [35 empty] | NO (may start in 2013)
| JDE Argentina | DS | [35 empty] | NO (may start in Sept 2013)
| Control M | DS | [35 empty] | TBD
| GPMR | DS | [35 empty] | No (may start in June 2013)
| FileMover | DS | [35 empty] | TBD
| MS SQL Server Integration Services (SSIS) | DS | [35 empty] | TBD
| App Colour Key |  | 9 | 11 | 17 | 15 | 16 | 16 | 17 | 18 | 19 | 19 | 16 | 19 | 20 | 20 | 22 | 20 | 20 | 20 | 21 | 18 | 16 | 15 | 19 | 12 | 10 | 6 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0
SCv2 apps
"Easy Wins"
SAP
No effort required
Q1 2013 new apps
Multiple locations
Date dependencies
|  |  | 0 | 0 | 2 | 0 | 2 | 1 | 6 | 0 | 4 | 6 | 0 | 1 | 2 | 1 | 4 | 0 | 5 | 2 | 3 | 3 | 3 | 0 | 7 | 2 | 4 | 2 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 2 | 2 | 4 | 5 | 11 | 11 | 15 | 21 | 21 | 22 | 24 | 25 | 29 | 29 | 34 | 36 | 39 | 42 | 45 | 45 | 52 | 54 | 58 | 60 | 60 | 60 | 60 | 64 | 64 | 64 | 64 | 64 | 64
Volume of On-boarding work over time

## Workdays (hidden)
| UAT | 1 | 2 | 3 | PROD | 1 | 2 | 3 | 4 | 5
Deployment 1 | #REF! | #REF! | #REF! | #REF! | 2014-03-20 | 12 | 13 | 14 | 15 | 16
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
0 | #REF! | #REF! | #REF! | #REF! | 0 | 1 | 2 | 3 | 4 | 5
0 | #REF! | #REF! | #REF! | #REF! | 0 | 1 | 2 | 3 | 4 | 5
0 | #REF! | #REF! | #REF! | #REF! | 0 | 1 | 2 | 3 | 4 | 5
0 | #REF! | #REF! | #REF! | #REF! | 0 | 1 | 2 | 3 | 4 | 5
0 | #REF! | #REF! | #REF! | #REF! | 0 | 1 | 2 | 3 | 4 | 5
0 | #REF! | #REF! | #REF! | #REF! | 0 | 1 | 2 | 3 | 4 | 5
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
0 | #REF! | #REF! | #REF! | #REF! | 0 | 1 | 2 | 3 | 4 | 5
0 | #REF! | #REF! | #REF! | #REF! | 0 | 1 | 2 | 3 | 4 | 5
0 | #REF! | #REF! | #REF! | #REF! | 0 | 1 | 2 | 3 | 4 | 5
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
0 | #REF! | #REF! | #REF! | #REF! | 0 | 1 | 2 | 3 | 4 | 5
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
0 | #REF! | #REF! | #REF! | #REF! | 0 | 1 | 2 | 3 | 4 | 5
0 | #REF! | #REF! | #REF! | #REF! | 0 | 1 | 2 | 3 | 4 | 5
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
0 | #REF! | #REF! | #REF! | #REF! | 0 | 1 | 2 | 3 | 4 | 5
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
0 | #REF! | #REF! | #REF! | #REF! | 0 | 1 | 2 | 3 | 4 | 5
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
0 | #REF! | #REF! | #REF! | #REF! | 0 | 1 | 2 | 3 | 4 | 5
0 | #REF! | #REF! | #REF! | #REF! | 0 | 1 | 2 | 3 | 4 | 5
0 | #REF! | #REF! | #REF! | #REF! | 0 | 1 | 2 | 3 | 4 | 5
0 | #REF! | #REF! | #REF! | #REF! | 0 | 1 | 2 | 3 | 4 | 5
0 | #REF! | #REF! | #REF! | #REF! | 0 | 1 | 2 | 3 | 4 | 5
0 | #REF! | #REF! | #REF! | #REF! | 0 | 1 | 2 | 3 | 4 | 5
0 | #REF! | #REF! | #REF! | #REF! | 0 | 1 | 2 | 3 | 4 | 5
0 | #REF! | #REF! | #REF! | #REF! | 0 | 1 | 2 | 3 | 4 | 5
0 | #REF! | #REF! | #REF! | #REF! | 0 | 1 | 2 | 3 | 4 | 5
0 | #REF! | #REF! | #REF! | #REF! | 0 | 1 | 2 | 3 | 4 | 5
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
0 | #REF! | #REF! | #REF! | #REF! | 0 | 1 | 2 | 3 | 4 | 5
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
0 | #REF! | #REF! | #REF! | #REF! | 0 | 1 | 2 | 3 | 4 | 5
0 | #REF! | #REF! | #REF! | #REF! | 0 | 1 | 2 | 3 | 4 | 5
0 | #REF! | #REF! | #REF! | #REF! | 0 | 1 | 2 | 3 | 4 | 5
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
0 | #REF! | #REF! | #REF! | #REF! | 0 | 1 | 2 | 3 | 4 | 5
0 | #REF! | #REF! | #REF! | #REF! | 0 | 1 | 2 | 3 | 4 | 5
0 | #REF! | #REF! | #REF! | #REF! | 0 | 1 | 2 | 3 | 4 | 5
0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
0 | #REF! | #REF! | #REF! | #REF! | 0 | 1 | 2 | 3 | 4 | 5
0 | #REF! | #REF! | #REF! | #REF! | 0 | 1 | 2 | 3 | 4 | 5
0 | #REF! | #REF! | #REF! | #REF! | 0 | 1 | 2 | 3 | 4 | 5
0 | #REF! | #REF! | #REF! | #REF! | 0 | 1 | 2 | 3 | 4 | 5
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
0 | #REF! | #REF! | #REF! | #REF! | 0 | 1 | 2 | 3 | 4 | 5
0 | #REF! | #REF! | #REF! | #REF! | 0 | 1 | 2 | 3 | 4 | 5
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
0 | #REF! | #REF! | #REF! | #REF! | 0 | 1 | 2 | 3 | 4 | 5
0 | #REF! | #REF! | #REF! | #REF! | 0 | 1 | 2 | 3 | 4 | 5

## Progress Tracker
Name | Date of pre-prod deployment | Date of Prod deployment | Date of Agent Install for Non-PROD | Next Action | Notes
Deployment 1 | 2014-01-06 | 2014-03-20
Deployment 2 | 2014-01-15 | 2014-03-20
Deployment 3 | 2014-01-18 | 2014-02-20
Deployment 4 | 2014-01-18 | 2014-02-20 |  | Request Change tickets to be raised by TSI. Schedule is on the handover notes.
Deployment 5 | 2014-02-14 | 2014-04-20 |  | Request Change tickets to be raised by TSI. Schedule is on the handover notes.
Deployment 6 | 2014-02-12 | 2014-04-15 |  | Request Change tickets to be raised by TSI. Schedule is on the handover notes.
Deployment 7 | 2014-02-07 | 2014-04-01
Deployment 8 | 2014-01-04 | 2014-04-07
Deployment 9 | 2014-01-04 | 2014-04-30
Deployment 10 | 2014-03-04 | 2014-04-20
Deployment 11 | 2014-03-15 | 2014-04-20
Deployment 12 | 2014-03-15 | 2014-04-20
Deployment 13 | 2014-02-09 | 2014-05-01
Deployment 14 | 2/1222014 | 2014-05-08
Deployment 15 | 2014-02-25 | 2014-05-16
Deployment 16 | 2014-02-25 | 2014-05-20
Deployment 17 | 2014-01-19 | 2014-02-20
Deployment 18 | 2014-01-18 | 2014-02-11
Deployment 19 | 2014-02-20 | 2014-04-30
Deployment 20 | 2014-02-06 | 2014-03-20
Deployment 21 | 2014-02-07 | 2014-04-01
Deployment 22 | 2014-02-08 | 2014-04-13
Ask TSI to provide print screen with Evidence of agent on-boarding.
The server is in support.
Testing complete
Chase business for a change window for production
Awaiting OB form from the business.
KB to ask T-Systems to run completion reports for this application
Make sure that by Friday we open the
The server is in support since 28 August.
Waiting for BO form from Mark Nye
Waiting for BO form from Mark Nye
KB to check if this is the same thing as shell people business warehouse?
KB to speak to Humayun for planning dates of installation. Discussion to take place in August.
KB to speak to Humayun for planning dates of installation. Discussion to take place in August.
Chase for OB form at start of October
Schedule UAT test

## Validations (hidden)
YES
NO

## Sheet1 (hidden)
Application Name | ID | BU
ArcSight | 167 | ITSO
ArcSight | 167 | ITSO
ArcSight | 167 | ITSO
BOS (Red Prairie Retail - Head Office) | 147 | DS
BOS (Red Prairie Retail - Head Office) | 147 | DS
BOS (Red Prairie Retail - Head Office) | 147 | DS
BOS (Red Prairie Retail - Head Office) | 147 | DS
BSI Tax Factory | 81 | GF
Collective (Archer) | 82 | GF
Collective (Archer) | 82 | GF
Collective (Archer) | 82 | GF
Contract Management System - Upside | 176 | GF
Contract Management System - Upside | 176 | GF
Contract Management System - Upside | 176 | GF
CONVERGE | 166 | UI
Customer Interaction Management (CIM) | 138 | DS
Customer Interaction Management (CIM) | 138 | DS
Customer Interaction Management (CIM) | 138 | DS
Customer Setup and Amend | 185 | DS
EDI Hub/ E Banking Hub | 83 | GF
eHaulier |  | DS
eMarketplace Suite | 127 | TR
eMarketplace Suite | 127 | TR
Endur Oil | 128 | TR
Energy Components (ALTAMIRA) | 97 | UI
Energy Components (EC-SEIC) | 98 | UI
Energy Components (GABON) | 99 | UI
Energy Components (KASHAGAN) | 100 | UI
Energy Components (MAJNOON) | 101 | UI
Energy Components (QSGTL) | 102 | UI
Energy Components (SPD) | 103 | UI
Energy Components (SPEX) | 104 | UI
Energy Components (STOS90) | 105 | UI
Energy Components (WGTEC-EC-UIE) | 106 | UI
Enterprise Business Objects Service (eBOSS) | 121 | GF
Enterprise Business Objects Service (eBOSS) | 121 | GF
Ergonomed | 78 | DS
Financial Closing Cockpit (FCC) | 85 | GF
Global Production Dashboard | 182 | UI
Global Production Dashboard | 182 | UI
GLS Toolset |  | PT
GLS Toolset |  | PT
GLS Toolset |  | PT
Identity Management Service (IMS) | 86 | GF
Identity Management Service (IMS) | 86 | GF
Identity Provider Service (IDP) | 87 | GF
Identity Provider Service (IDP) | 87 | GF
KSTAT | 180 | TR
MS SQL Server Integration Services (SSIS) | 142 | DS
MS SQL Server Integration Services (SSIS) | 142 | DS
ODW | 129 | TR
PRISM |  | UA
PRT-NEWSUM (New Servers) |  | UI
Sabrix - GF | 137 | GF
Sabrix - GF | 137 | GF
SAP GRC (PG4) | 186 | GF
SAP US Luminon BW Syst |  | DS
SAP US Luminon Syst |  | DS
SAP US Magellan Syst |  | DS
SAP US Simon Bolt |  | DS
Shell eServe |  | DS
Shell People Business Warehouse | 89 | GF
SHELL PEOPLE HR Reporting | 90 | GF
SODA | 130 | TR
STACA |  | UI
TRIM (non-MC) | 122 | GF
TRIM (non-MC) | 122 | GF
TRIM (non-MC) | 122 | GF
TRIM (non-MC) | 122 | GF
TSI | 91 | GF

## Sheet2 (hidden)
AGRisk/Quantum | 88
AGRisk/Quantum | 88
AGRisk/Quantum | 88
AGRisk/Quantum | 88
ArcSight | 167
ArcSight | 167
ArcSight | 167
BOS (Red Prairie Retail - Head Office) | 147
BSI Tax Factory | 81
Collective (Archer) | 82
Collective (Archer) | 82
Collective (Archer) | 82
Contract Management System - Upside | 176
Contract Management System - Upside | 176
Contract Management System - Upside | 176
CONVERGE | 166
Customer Setup and Amend | 185
EDI Hub/ E Banking Hub | 83
eHaulier | 150
eMarketplace Suite | 127
eMarketplace Suite | 127
Endur Oil | 128
Endur Oil | 128
Endur Oil | 128
Endur Oil | 128
Energy Components (ALTAMIRA) | 97
Energy Components (EC-SEIC) | 98
Energy Components (GABON) | 99
Energy Components (KASHAGAN) | 100
Energy Components (MAJNOON) | 101
Energy Components (QSGTL) | 102
Energy Components (SPD) | 103
Energy Components (SPEX) | 104
Energy Components (STOS90) | 105
Energy Components (WGTEC-EC-UIE) | 106
ENOM | 96
Enterprise Business Objects Service (eBOSS) | 121
Enterprise Business Objects Service (eBOSS) | 121
Ergonomed | 78
ERS - Enterprise Reporting Solution (ERS) | 84
Financial Closing Cockpit (FCC) | 85
Financial Closing Cockpit (FCC) | 85
Financial Closing Cockpit (FCC) | 85
Global ICEBOX (P2 instances) | SHELL
Global ICEBOX (P4 instances) | SHELL
Global Production Dashboard | 182
Global Production Dashboard | 182
GLS Toolset | 94
GLS Toolset | 94
GLS Toolset | 94
GLS Toolset | 94
GLS Toolset | 94
Identity Management Service (IMS) | 86
Identity Management Service (IMS) | 86
Identity Management Service (IMS) | 86
Identity Provider Service (IDP) | 87
Identity Provider Service (IDP) | 87
KSTAT | 180
LIFETIME | 132
MC GFM | 168
MC GFM | 168
MC Petrolook | 174
MC Sharepoint | SHELL
MC Sigma | 173
MC Sigma | 173
ODW | 129
ODW | 129
ODW | 129
ODW | 129
Pearl SAMCO including Batch processes | 133
ProWatch (new servers) | SHELL
SABRIX | 114
SAP BUSINESS WAREHOUSE | SHELL
SAP GRC (PG4) | 186
SAP US Luminon BW Syst | SHELL
SAP US Luminon Syst | SHELL
SAP US Magellan Syst | SHELL
SAP US Simon Bolt | SHELL
SAP::CRM::CHM | SHELL
SHARE St. Rose | SHELL
Sharepoint 2010 | SHELL
Shell eServe | 161
Shell People Business Warehouse | 89
Shell People Business Warehouse | 89
SHELL PEOPLE HR Reporting | 90
SHELL PEOPLE HR Reporting | 90
Simcorp Dimension including Batch processes, Models and PIP | 134
SODA | 130
SPOTFIRE MC | SHELL
SPOTFIRE MC | SHELL
SWIFT (SAMCO) | 135
TRIM (non-MC) | 122
TSI | 91
TSI | 91
Vertex Bolt-on | SHELL
Vertex Bolt-on (Lumminon) | SHELL
PRT-NEWSUM | SHELL

## Sheet5 (hidden)
Awaiting OB Form
Testing Stage
Production Stage
Acceptance Stage
Completed

## Visual
Project |  |  | JAN |  |  |  |  | FEB |  |  |  | MAR |  |  |  |  | APR |  |  |  | MAY |  |  |  | JUN
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27
| Deployment 1 |  | JAN 2: U; JAN 3: U; JAN 4: U; MAR 12: P; MAR 13: P; MAR 14: P; APR 15: P; APR 16: P; APR 17: C
| Deployment 2 |  | JAN 3: U; JAN 4: U; JAN 5: U; MAR 12: P; MAR 13: P; MAR 14: P; APR 15: P; APR 16: P; APR 17: C
| Deployment 3 |  | JAN 3: U; JAN 4: U; JAN 5: U; FEB 8: P; FEB 9: P; MAR 10: P; MAR 11: P; MAR 12: P; MAR 13: C
| Deployment 4 |  | JAN 3: U; JAN 4: U; JAN 5: U; FEB 8: P; FEB 9: P; MAR 10: P; MAR 11: P; MAR 12: P; MAR 13: C
| Deployment 5 |  | FEB 7: U; FEB 8: U; FEB 9: U; APR 16: P; APR 17: P; APR 18: P; MAY 19: P; MAY 20: P; MAY 21: C
| Deployment 6 |  | FEB 7: U; FEB 8: U; FEB 9: U; APR 16: P; APR 17: P; APR 18: P; MAY 19: P; MAY 20: P; MAY 21: C
| Deployment 7 |  | FEB 6: U; FEB 7: U; FEB 8: U; MAR 14: P; APR 15: P; APR 16: P; APR 17: P; APR 18: P; MAY 19: C
| Deployment 8 |  | JAN 1: U; JAN 2: U; JAN 3: U; APR 15: P; APR 16: P; APR 17: P; APR 18: P; MAY 19: P; MAY 20: C
| Deployment 9 |  | JAN 1: U; JAN 2: U; JAN 3: U; APR 18: P; MAY 19: P; MAY 20: P; MAY 21: P; MAY 22: P; JUN 23: C
| Deployment 10 |  | MAR 10: U; MAR 11: U; MAR 12: U; APR 16: P; APR 17: P; APR 18: P; MAY 19: P; MAY 20: P; MAY 21: C
| Deployment 11 |  | MAR 11: U; MAR 12: U; MAR 13: U; APR 16: P; APR 17: P; APR 18: P; MAY 19: P; MAY 20: P; MAY 21: C
| Deployment 12 |  | MAR 11: U; MAR 12: U; MAR 13: U; APR 16: P; APR 17: P; APR 18: P; MAY 19: P; MAY 20: P; MAY 21: C
| Deployment 13 |  | FEB 6: U; FEB 7: U; FEB 8: U; APR 18: P; MAY 19: P; MAY 20: P; MAY 21: P; MAY 22: P; JUN 23: C
Deployment 14 | bar: MAY 19 to JUN 24
| Deployment 15 |  | FEB 9: U; MAR 10: U; MAR 11: U; MAY 20: P; MAY 21: P; MAY 22: P; JUN 23: P; JUN 24: P; JUN 25: C
| Deployment 16 |  | FEB 9: U; MAR 10: U; MAR 11: U; MAY 21: P; MAY 22: P; JUN 23: P; JUN 24: P; JUN 25: P; JUN 26: C
| Deployment 17 |  | JAN 3: U; JAN 4: U; JAN 5: U; FEB 8: P; FEB 9: P; MAR 10: P; MAR 11: P; MAR 12: P; MAR 13: C
| Deployment 18 |  | JAN 3: U; JAN 4: U; JAN 5: U; FEB 7: P; FEB 8: P; FEB 9: P; MAR 10: P; MAR 11: P; MAR 12: C
| Deployment 19 |  | FEB 8: U; FEB 9: U; MAR 10: U; APR 18: P; MAY 19: P; MAY 20: P; MAY 21: P; MAY 22: P; JUN 23: C
| Deployment 20 |  | FEB 6: U; FEB 7: U; FEB 8: U; MAR 12: P; MAR 13: P; MAR 14: P; APR 15: P; APR 16: P; APR 17: C
| Deployment 21 |  | FEB 6: U; FEB 7: U; FEB 8: U; MAR 14: P; APR 15: P; APR 16: P; APR 17: P; APR 18: P; MAY 19: C
| Deployment 22 |  | FEB 6: U; FEB 7: U; FEB 8: U; APR 15: P; APR 16: P; APR 17: P; APR 18: P; MAY 19: P; MAY 20: C
|  | UAT | 2 | 3 | 8 | 6 | 5 | 5 | 7 | 8 | 5 | 4 | 5 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PROD | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 4 | 4 | 4 | 4 | 6 | 3 | 5 | 7 | 12 | 9 | 12 | 11 | 10 | 6 | 6 | 3 | 2 | 1 | 0 | 0
|  | Total | 2 | 3 | 8 | 6 | 5 | 5 | 8 | 12 | 9 | 8 | 9 | 9 | 5 | 5 | 7 | 12 | 9 | 12 | 11 | 10 | 6 | 6 | 3 | 2 | 1 | 0 | 0
|  | Day 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 0 | 0 | 0 | 3 | 0 | 2 | 2 | 5 | 0 | 3 | 1 | 1 | 1 | 0
|  | Day 0 ALL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 4 | 4 | 4 | 4 | 7 | 7 | 9 | 11 | 16 | 16 | 19 | 20 | 21 | 22 | 22
|  | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 0 | 0 | 0 | 3 | 0 | 2 | 2 | 5 | 0 | 3 | 1 | 1 | 1 | 0
|  | Actual All | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 4 | 4 | 4 | 4 | 7 | 7 | 9 | 11 | 16 | 16 | 19 | 20 | 21 | 22 | 22
Volume of work over time

## Sys
| UAT | 1 | 2 | 3 | PROD
Deployment 1 | 2014-01-06 | 2 | 3 | 4 | 2014-03-20 | 12 | 13 | 14 | 15 | 16
Deployment 2 | 2014-01-15 | 3 | 4 | 5 | 2014-03-20 | 12 | 13 | 14 | 15 | 16
Deployment 3 | 2014-01-18 | 3 | 4 | 5 | 2014-02-20 | 8 | 9 | 10 | 11 | 12
Deployment 4 | 2014-01-18 | 3 | 4 | 5 | 2014-02-20 | 8 | 9 | 10 | 11 | 12
Deployment 5 | 2014-02-14 | 7 | 8 | 9 | 2014-04-20 | 16 | 17 | 18 | 19 | 20
Deployment 6 | 2014-02-12 | 7 | 8 | 9 | 2014-04-15 | 16 | 17 | 18 | 19 | 20
Deployment 7 | 2014-02-07 | 6 | 7 | 8 | 2014-04-01 | 14 | 15 | 16 | 17 | 18
Deployment 8 | 2014-01-04 | 1 | 2 | 3 | 2014-04-07 | 15 | 16 | 17 | 18 | 19
Deployment 9 | 2014-01-04 | 1 | 2 | 3 | 2014-04-30 | 18 | 19 | 20 | 21 | 22
Deployment 10 | 2014-03-04 | 10 | 11 | 12 | 2014-04-20 | 16 | 17 | 18 | 19 | 20
Deployment 11 | 2014-03-15 | 11 | 12 | 13 | 2014-04-20 | 16 | 17 | 18 | 19 | 20
Deployment 12 | 2014-03-15 | 11 | 12 | 13 | 2014-04-20 | 16 | 17 | 18 | 19 | 20
Deployment 13 | 2014-02-09 | 6 | 7 | 8 | 2014-05-01 | 18 | 19 | 20 | 21 | 22
Deployment 14 | 2/1222014 |  |  |  | 2014-05-08 | 19 | 20 | 21 | 22 | 23
Deployment 15 | 2014-02-25 | 9 | 10 | 11 | 2014-05-16 | 20 | 21 | 22 | 23 | 24
Deployment 16 | 2014-02-25 | 9 | 10 | 11 | 2014-05-20 | 21 | 22 | 23 | 24 | 25
Deployment 17 | 2014-01-19 | 3 | 4 | 5 | 2014-02-20 | 8 | 9 | 10 | 11 | 12
Deployment 18 | 2014-01-18 | 3 | 4 | 5 | 2014-02-11 | 7 | 8 | 9 | 10 | 11
Deployment 19 | 2014-02-20 | 8 | 9 | 10 | 2014-04-30 | 18 | 19 | 20 | 21 | 22
Deployment 20 | 2014-02-06 | 6 | 7 | 8 | 2014-03-20 | 12 | 13 | 14 | 15 | 16
Deployment 21 | 2014-02-07 | 6 | 7 | 8 | 2014-04-01 | 14 | 15 | 16 | 17 | 18
Deployment 22 | 2014-02-08 | 6 | 7 | 8 | 2014-04-13 | 15 | 16 | 17 | 18 | 19